## BLANK ONE SPOR Chart & Burndown
SCRUM PROJECT MANAGEMENT ONE SPORT CHART
ONE SPORT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATED | COMPLETED | REMAINING | [5 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Setup of the environment |  | 45 | 45 | 0 |  |  |  | 4 | 100%
1.1 | Database + containerization of DB |  | 10 | 10 | 0 | 1 |  |  | 1 | 100% | bar: WEEK 1 M to WEEK 1 T
1.2 | Setup of preliminary containers |  | 10 | 10 | 0 | 1 |  |  | 1 | 100% | bar: WEEK 1 M to WEEK 1 T
1.3 | Connecting all the preliminary microservices |  | 15 | 15 | 0 | 1 |  |  | 1 | 100% | bar: WEEK 1 W to WEEK 2 F
1.4 | Login + Logout setup |  | 10 | 10 | 0 | 1 |  |  | 1 | 100%
2 | Backend development |  | 30 | 25 | 5 |  |  |  | 9 | 83.33%
2.1 | Authentication Microservice |  | 10 | 10 | 0 | 2 |  |  | 1 | 100% | bar: WEEK 2 M to WEEK 3 T
2.2 | Notification Microservice |  | 10 | 10 | 0 | 2 |  |  | 1 | 100% | bar: WEEK 3 W to WEEK 3 T
2.3 | TO INVENT |  |  |  | 0 | 2 |  |  | 2 | #DIV/0! | bar: WEEK 3 T to WEEK 3 F
2.4 | Testing |  | 5 | 5 | 0 | 2 |  |  | 1 | 100% | bar: WEEK 4 M to WEEK 4 W
2.5 |  |  | 5 |  | 5 | 2 |  |  | 1 | 0% | bar: WEEK 4 T to WEEK 5 F
3 | Frontend development |  | 55 | 55 | 0 |  |  |  | 17 | 100%
3.1 | Profile |  | 5 | 5 | 0 | 3 |  |  | 1 | 100%
3.2 | Reports |  | 15 | 15 | 0 | 3 |  |  | 1 | 100%
3.3 | Map |  | 20 | 20 | 0 | 3 |  |  | 1 | 100%
3.4 | Dashboard |  | 10 | 10 | 0 | 3 |  |  | 1 | 100% | bar: WEEK 5 M to WEEK 6 T
3.5 | Testing |  | 5 | 5 | 0 | 3 |  |  | 1 | 100% | bar: WEEK 6 W to WEEK 6 F
4 | Finalization of functionalities and testing |  | 14 | 14 | 0 |  |  |  | 13 | 100%
4.1 | Testing of Profile section |  | 3 | 3 | 0 | 4 |  |  | 1 | 100%
4.2 | Testing of Report section |  | 3 | 3 | 0 | 4 |  |  | 1 | 100%
4.3 | Testing of Map view |  | 5 | 5 | 0 | 4 |  |  | 1 | 100% | bar: WEEK 11 M to WEEK 12 T
4.4 | Testing of Notifications |  | 3 | 3 | 0 | 4 |  |  | 1 | 100% | bar: WEEK 12 W to WEEK 12 F
4.4 | Testing of Dashboard |  | 2 | 2 | 0 | 4 |  |  | 1 | 100% | bar: WEEK 12 W to WEEK 12 F
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS worked in total (if we worked the same day we count it as 1 day) | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 499 | 474 | 15 | 66 | 7.5606 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | [10 empty] | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 499 | 499 | 499 | 499 | 491.4394 | 483.8788 | 476.3182 | 468.7576 | 461.197 | 453.6364 | 446.0758 | 438.5152 | 430.9545 | 423.3939 | 415.8333 | 408.2727 | 400.7121 | 393.1515 | 385.5909 | 378.0303 | 370.4697 | 362.9091 | 355.3485 | 347.7879 | 340.2273 | 332.6667 | 325.1061 | 317.5455 | 309.9848 | 302.4242 | 294.8636 | 287.303 | 279.7424 | 272.1818 | 264.6212 | 257.0606 | 249.5 | 241.9394 | 234.3788 | 226.8182 | 219.2576 | 211.697 | 204.1364 | 196.5758 | 189.0152 | 181.4545 | 173.8939 | 166.3333 | 158.7727 | 151.2121
[10 empty] | ESTIMATE | 499 | 496 | 493 | 499 | 494 | 489 | 486 | 483 | 480 | 474 | 471 | 467 | 461 | 454 | 449 | 444 | 439 | 434 | 429 | 426 | 423 | 420 | 416 | 413 | 409 | 405 | 402 | 399 | 396 | 393 | 390 | 386 | 382 | 378 | 374 | 366 | 359 | 355 | 351 | 347 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | [10 empty] | 19083
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 3 | 3 | 3 | 5 | 5 | 3 | 3 | 3 | 6 | 3 | 4 | 6 | 7 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 4 | 3 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 8 | 7 | 4 | 4 | 4 | 3 | [20 empty] | 155
[10 empty] | HRS REMAINING | 496 | 493 | 490 | 494 | 489 | 486 | 483 | 480 | 474 | 471 | 467 | 461 | 454 | 449 | 444 | 439 | 434 | 429 | 426 | 423 | 420 | 416 | 413 | 409 | 405 | 402 | 399 | 396 | 393 | 390 | 386 | 382 | 378 | 374 | 366 | 359 | 355 | 351 | 347 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | 344 | [10 empty] | 18928
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT ONE SPORT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
High | 1 | Having the whole environment ready | Setup of the Environment | In this sprint our objective was to have all the basics structure implemented |  | 8 | Completed |  | Not Started | 1
High | 2 | Implementing the backend functionalities | Backend Development | We exclusively focused on the microservices' backend |  | 24 | In Progress |  | In Progress | 2
High | 3 | Implementing the frontend functionalities | Frontend Development | We utilized TODO to create the Frontend pages, and we also added the necessary external API to backend features. |  | 40 | In Progress |  | Completed | 4
Medium | 4 | Finalization of the system | Finalization and testing | Execution of the final features, comprehensive testing of both the features and the fully deployed system. |  | 16 | Not Started |  |  | 8
16
24
40
80