## Chart & Burndown
SCRUM PROJECT MANAGEMENT ONE SPORT CHART
ONE SPORT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATED | COMPLETED | REMAINING | [5 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Setup of the environment |  | 65 | 65 | 0 |  |  |  | 14 | 100%
1.1 | Documentation and planning | Zizzo | 20 | 20 | 0 | 1 | 2024-08-26 | 2024-08-28 | 3 | 100% | bar: WEEK 1 M to WEEK 1 W
1.2 | Database + containerization of DB | Carrozzo | 10 | 10 | 0 | 1 | 2024-08-27 | 2024-08-29 | 3 | 100% | bar: WEEK 1 T to WEEK 1 T
1.3 | Setup of preliminary containers | Carrozzo | 10 | 10 | 0 | 1 | 2024-08-29 | 2024-08-30 | 2 | 100% | bar: WEEK 1 T to WEEK 2 F
1.4 | Connecting all the preliminary microservices | Carrozzo | 15 | 15 | 0 | 1 | 2024-09-02 | 2024-09-04 | 3 | 100%
1.5 | Login + Logout setup | Carrozzo | 10 | 10 | 0 | 1 | 2024-09-04 | 2024-09-06 | 3 | 100%
2 | Backend development |  | 75 | 75 | 0 |  |  |  | 9 | 100%
2.1 | Authentication Microservice | Carrozzo | 15 | 15 | 0 | 2 | 2024-09-09 | 2024-09-11 | 3 | 100% | bar: WEEK 2 M to WEEK 3 W
2.2 | Reports | Pascucci | 10 | 10 | 0 | 2 | 2024-09-09 | 2024-09-10 | 2 | 100% | bar: WEEK 2 M to WEEK 3 T
2.3 | Notification Microservice | Carrozzo | 15 | 15 | 0 | 2 | 2024-09-12 | 2024-09-16 | 2 | 100% | bar: WEEK 3 T to WEEK 4 M
2.4 | Map | Carrozzo | 20 | 20 | 0 | 2 | 2024-09-16 | 2024-09-19 | 4 | 100% | bar: WEEK 4 M to WEEK 4 T
2.5 | Follow Microservice | Carrozzo | 10 | 10 | 0 | 2 | 2024-09-19 | 2024-09-20 | 2 | 100% | bar: WEEK 4 T to WEEK 5 F
2.6 | Admin dashboard | Zizzo | 5 | 5 | 0 | 2 | 2024-09-20 | 2024-09-20 | 1 | 100% | bar: WEEK 4 F to WEEK 5 F
3 | Frontend development |  | 55 | 55 | 0 |  |  |  | 17 | 100%
3.1 | Profile | Carrozzo | 5 | 5 | 0 | 3 | 2024-09-23 | 2024-09-23 | 1 | 100%
3.2 | Reports | Pascucci | 15 | 15 | 0 | 3 | 2024-09-23 | 2024-09-25 | 3 | 100%
3.3 | Map | Carrozzo | 20 | 20 | 0 | 3 | 2024-09-24 | 2024-09-27 | 4 | 100%
3.4 | Admin dashboard | Zizzo | 10 | 10 | 0 | 3 | 2024-09-23 | 2024-09-25 | 3 | 100%
3.5 | Testing | Pascucci + Zizzo | 5 | 5 | 0 | 3 | 2024-09-26 | 2024-09-27 | 2 | 100%
4 | Finalization of functionalities and testing |  | 13 | 13 | 0 |  |  |  | 13 | 100%
4.1 | Testing of Profile section | Carrozzo | 1 | 1 | 0 | 4 | 2024-10-07 | 2024-10-07 | 1 | 100% | bar: WEEK 7 M
4.2 | Testing of Report section | Pascucci | 3 | 3 | 0 | 4 | 2024-10-08 | 2024-10-08 | 1 | 100% | bar: WEEK 7 T
4.3 | Testing of Map view | Carrozzo | 4 | 4 | 0 | 4 | 2024-10-09 | 2024-10-09 | 1 | 100% | bar: WEEK 7 W
4.4 | Testing of Notifications and Follows | Carrozzo | 5 | 5 | 0 | 4 | 2024-10-10 | 2024-10-10 | 1 | 100% | bar: WEEK 7 W
4.4 | Testing of Dashboard | Zizzo | 2 | 2 | 0 | 4 | 2024-10-10 | 2024-10-10 | 1 | 100% | bar: WEEK 7 W
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS worked in total (if we worked the same day we count it as 1 day) | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 756 | 756 | 0 | 66 | 11.4545 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | [10 empty] | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 756 | 756 | 756 | 756 | 744.5455 | 733.0909 | 721.6364 | 710.1818 | 698.7273 | 687.2727 | 675.8182 | 664.3636 | 652.9091 | 641.4545 | 630 | 618.5455 | 607.0909 | 595.6364 | 584.1818 | 572.7273 | 561.2727 | 549.8182 | 538.3636 | 526.9091 | 515.4545 | 504 | 492.5455 | 481.0909 | 469.6364 | 458.1818 | 446.7273 | 435.2727 | 423.8182 | 412.3636 | 400.9091 | 389.4545 | 378 | 366.5455 | 355.0909 | 343.6364 | 332.1818 | 320.7273 | 309.2727 | 297.8182 | 286.3636 | 274.9091 | 263.4545 | 252 | 240.5455 | 229.0909
[10 empty] | ESTIMATE | 756 | 753 | 750 | 756 | 751 | 746 | 743 | 740 | 737 | 731 | 728 | 724 | 718 | 711 | 706 | 701 | 696 | 691 | 686 | 683 | 680 | 677 | 673 | 670 | 666 | 662 | 659 | 656 | 653 | 650 | 647 | 643 | 639 | 635 | 631 | 623 | 616 | 612 | 608 | 604 | 601 | 601 | 601 | 601 | 601 | 601 | 601 | 601 | 601 | 601 | [10 empty] | 31162
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 3 | 3 | 3 | 5 | 5 | 3 | 3 | 3 | 6 | 3 | 4 | 6 | 7 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 4 | 3 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 8 | 7 | 4 | 4 | 4 | 3 | [20 empty] | 155
[10 empty] | HRS REMAINING | 753 | 750 | 747 | 751 | 746 | 743 | 740 | 737 | 731 | 728 | 724 | 718 | 711 | 706 | 701 | 696 | 691 | 686 | 683 | 680 | 677 | 673 | 670 | 666 | 662 | 659 | 656 | 653 | 650 | 647 | 643 | 639 | 635 | 631 | 623 | 616 | 612 | 608 | 604 | 601 | 601 | 601 | 601 | 601 | 601 | 601 | 601 | 601 | 601 | 601 | [10 empty] | 31007
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT ONE SPORT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
High | 1 | Having the whole environment ready | Setup of the Environment | In this sprint our objective was to have all the basics structure implemented and documentation ready |  | 40 | Completed |  | Not Started | 1
High | 2 | Implementing the backend functionalities | Backend Development | We exclusively focused on the microservices' backend |  | 80 | Completed |  | In Progress | 2
High | 3 | Implementing the frontend functionalities | Frontend Development | We utilized React to create the Frontend pages |  | 40 | Completed |  | Completed | 4
Medium | 4 | Finalization of the system | Finalization and testing | Execution of the final features, comprehensive testing of both the features and the fully deployed system. |  | 40 | Completed |  |  | 8
16
24
40
80