## Chart & Burndown
SCRUM PROJECT MANAGEMENT URBAN WATCH CHART
URBAN WATCH CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATED | COMPLETED | REMAINING | [5 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Setup of the environment |  | 65 | 65 | 0 |  |  |  | 14 | 100%
1.1 | Documentation and planning | Zizzo | 20 | 20 | 0 | 1 | 2024-08-26 | 2024-08-28 | 3 | 100% | bar: WEEK 1 M to WEEK 1 W
1.2 | Database + containerization of DB | Carrozzo | 10 | 10 | 0 | 1 | 2024-08-27 | 2024-08-29 | 3 | 100% | bar: WEEK 1 T to WEEK 1 T
1.3 | Setup of preliminary containers | Carrozzo | 10 | 10 | 0 | 1 | 2024-08-29 | 2024-08-30 | 2 | 100% | bar: WEEK 1 T to WEEK 2 F
1.4 | Connecting all the preliminary microservices | Carrozzo | 15 | 15 | 0 | 1 | 2024-09-02 | 2024-09-04 | 3 | 100%
1.5 | Login + Logout setup | Carrozzo | 10 | 10 | 0 | 1 | 2024-09-04 | 2024-09-06 | 3 | 100%
2 | Backend development |  | 75 | 75 | 0 |  |  |  | 14 | 100%
2.1 | Authentication Microservice | Carrozzo | 15 | 15 | 0 | 2 | 2024-09-09 | 2024-09-11 | 3 | 100% | bar: WEEK 2 M to WEEK 3 W
2.2 | Report Microservice | Pascucci + Carrozzo | 10 | 10 | 0 | 2 | 2024-09-09 | 2024-09-10 | 2 | 100% | bar: WEEK 2 M to WEEK 3 T
2.3 | Notification Microservice | Carrozzo | 15 | 15 | 0 | 2 | 2024-09-12 | 2024-09-16 | 2 | 100% | bar: WEEK 3 T to WEEK 4 M
2.4 | Map | Carrozzo | 20 | 20 | 0 | 2 | 2024-09-16 | 2024-09-19 | 4 | 100% | bar: WEEK 4 M to WEEK 4 T
2.5 | Follow Microservice | Carrozzo | 10 | 10 | 0 | 2 | 2024-09-19 | 2024-09-20 | 2 | 100% | bar: WEEK 4 T to WEEK 5 F
2.6 | Admin dashboard | Zizzo | 5 | 5 | 0 | 2 | 2024-09-20 | 2024-09-20 | 1 | 100% | bar: WEEK 4 F to WEEK 5 F
3 | Frontend development |  | 55 | 55 | 0 |  |  |  | 13 | 100%
3.1 | Profile | Carrozzo | 5 | 5 | 0 | 3 | 2024-09-23 | 2024-09-23 | 1 | 100%
3.2 | Reports | Pascucci | 15 | 15 | 0 | 3 | 2024-09-23 | 2024-09-25 | 3 | 100%
3.3 | Map | Carrozzo | 20 | 20 | 0 | 3 | 2024-09-24 | 2024-09-27 | 4 | 100%
3.4 | Admin dashboard | Zizzo | 10 | 10 | 0 | 3 | 2024-09-23 | 2024-09-25 | 3 | 100%
3.5 | Testing | Pascucci + Zizzo | 5 | 5 | 0 | 3 | 2024-09-26 | 2024-09-27 | 2 | 100%
4 | Finalization of functionalities and testing |  | 15 | 15 | 0 |  |  |  | 5 | 100%
4.1 | Testing of Profile section | Carrozzo | 1 | 1 | 0 | 4 | 2024-10-07 | 2024-10-07 | 1 | 100% | bar: WEEK 7 M
4.2 | Testing of Report section | Pascucci | 3 | 3 | 0 | 4 | 2024-10-08 | 2024-10-08 | 1 | 100% | bar: WEEK 7 T
4.3 | Testing of Map view | Carrozzo | 4 | 4 | 0 | 4 | 2024-10-09 | 2024-10-09 | 1 | 100% | bar: WEEK 7 W
4.4 | Testing of Notifications and Follows | Carrozzo | 5 | 5 | 0 | 4 | 2024-10-10 | 2024-10-10 | 1 | 100% | bar: WEEK 7 W
4.4 | Testing of Dashboard | Zizzo | 2 | 2 | 0 | 4 | 2024-10-10 | 2024-10-10 | 1 | 100% | bar: WEEK 7 W
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS worked in total (if we worked the same day we count it as 1 day) | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 210 | 210 | 0 | 28 | 7.5 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | [10 empty] | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 210 | 210 | 210 | 210 | 202.5 | 195 | 187.5 | 180 | 172.5 | 165 | 157.5 | 150 | 142.5 | 135 | 127.5 | 120 | 112.5 | 105 | 97.5 | 90 | 82.5 | 75 | 67.5 | 60 | 52.5 | 45 | 37.5 | 30 | 22.5 | 15 | 7.5 | 0 | -7.5 | -15 | -22.5 | -30 | -37.5 | -45 | -52.5 | -60 | -67.5 | -75 | -82.5 | -90 | -97.5 | -105 | -112.5 | -120 | -127.5 | -135
[10 empty] | ESTIMATE | 210 | 203 | 193 | 184 | 175 | 170 | 165 | 160 | 154 | 150 | 145 | 135 | 125 | 120 | 115 | 110 | 100 | 95 | 90 | 80 | 70 | 56 | 43 | 30 | 23 | 15 | 15 | 15 | 15 | 15 | 15 | 14 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 2610
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | WEEK 1 M: 7; WEEK 1 T: 10; WEEK 1 W: 9; WEEK 1 T: 9; WEEK 1 F: 5; WEEK 2 M: 5; WEEK 2 T: 5; WEEK 2 W: 6; WEEK 2 T: 4; WEEK 2 F: 5; WEEK 3 M: 10; WEEK 3 T: 10; WEEK 3 W: 5; WEEK 3 T: 5; WEEK 3 F: 5; WEEK 4 M: 10; WEEK 4 T: 5; WEEK 4 W: 5; WEEK 4 T: 10; WEEK 4 F: 10; WEEK 5 M: 14; WEEK 5 T: 13; WEEK 5 W: 13; WEEK 5 T: 7; WEEK 5 F: 8; WEEK 7 M: 1; WEEK 7 T: 3; WEEK 7 W: 11 | 184
[10 empty] | HRS REMAINING | 203 | 193 | 184 | 175 | 170 | 165 | 160 | 154 | 150 | 145 | 135 | 125 | 120 | 115 | 110 | 100 | 95 | 90 | 80 | 70 | 56 | 43 | 30 | 23 | 15 | 15 | 15 | 15 | 15 | 15 | 14 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 2426
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT URBAN WATCH CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
High | 1 | Having the whole environment ready | Setup of the Environment | In this sprint our objective was to have all the basics structure implemented and documentation ready |  | 40 | Completed |  | Not Started | 1
High | 2 | Implementing the backend functionalities | Backend Development | We exclusively focused on the microservices' backend |  | 80 | Completed |  | In Progress | 2
High | 3 | Implementing the frontend functionalities | Frontend Development | We utilized React to create the Frontend pages |  | 40 | Completed |  | Completed | 4
Medium | 4 | Finalization of the system | Finalization and testing | Execution of the final features, comprehensive testing of both the features and the fully deployed system. |  | 40 | Completed |  |  | 8
16
24
40
80